## Sheet1
Section | Description | Jevin comments (13.03.2025) | SRP comments (07.04.2025) | Jevin comments (16.04.2025) | SRP comments (17.04.2025) | Jevin comments (05.05.2025) | SRP comments (09.05.2025) | Jevin comments (13.05.2025) | SRP comments (28.05.2025) | Jevin comments (05.06.2025) | SRP comments (19.11.2025)
1.1 | Cover letter | Please sign off Cover Letter. | Attached | Ok, this point is cleared.
1.4.1 | Outer Carton |  |  | New design of the outer carton was given for Sitagliptin 50mg and 100mg. Please confirm that the latest artworks given will be used for submission instead of the original outer carton artwork given in the dossier? | use the new design instead of the one inside the dossier. | Ok, this point is cleared.
1.4.2 | Inner/ Blister Label | Please provide the Inner/ Blister label artwork (50mg and 100mg). | Check in the Folder Artwork in the share folder https://srgpharmaceuticals-my.sharepoint.com/my?id=%2Fpersonal%2Frizal%5Fsrgpharmaceuticals%5Fcom%2FDocuments%2FSingapore%2FArtwork | Ok, this point is cleared.
1.7 | Description of batch numbering system | Please provide the Batch Numbering System SOP. | Will request from supplier | Pending | Batch Numbering System SOP provided in FP-Annex-1 | Ok, this point is cleared.
1.8 | Proof of Approval | Please provide the approval letter in a colour scanned copy of either the original copy or a certified true copy of the original doc. | Will request from supplier | Pending | API-Annexure 1 | Proof of Approval in a coloured scanned copy of either the original copy or a certified true copy of the original doc, is not not given. Please see attached black and white copy for reference. | Pending | Please send colored CoPP for 100mg. | Attached | CoPP for both strengths have expired. (Valid until 29.05.25) Please send me a new, updated CoPP. | Attached
1.9 | GMP certificate | Please provide GMP certificate (PICs copy) from the API manufacturer (Lee Pharma). | Will request from supplier | Pending | API manufacturing facility has been inspected with France and EDQM and our facility has been certified with Eudra GMP certificate, which is provided in API-Annexure-II. | Ok, this point is cleared.
1.10.2 | Authorisation Letter from Product Owner to the Manufacturer(s) | Please sign off this letter. | Attached | Ok, this point is cleared.
1.12 | Patent Declaration Form | Please sign off this form (page 4 only). | Attached | Ok, this point is cleared.
1.12 | Patent Declaration Form | Please submit a copy of SRG ACRA BIZ file | Attached | Ok, this point is cleared.
1.13 | Declaration on rejection, withdrawal and deferral | Please sign off this letter | Attached | Ok, this point is cleared.
1.15 | Registration Status in Other Countries | Please fill up this form | Not registered in any other country, only registered for manufacturing in India for Export Only | Please fill up the information in the yellow row. | Attached please check if acceptable | Please fill according to this format: 1.Country: List down the country that the product was approved in 2.Application status: Please state Approved/ Reject? 3.Status Date: Please state down the date of approval 4.Approved application… details: List down fully the indication in the form 5. Approved application.. details: List down the dosing in the form. **Note: Please do not convert it to pdf and leave it in word format. | Attached 1.15 Registration Status Sitagliptin v1 | Ok, this point is cleared.
S | CEP | Please provide CEP from Lee Pharma, if its available. | Will request supplier to provide | Pending | API-Annexure 1 | Ok, this point is cleared.
S2.2 | Description of Manufacturing Process and Process Controls | Using document: S2.2 Description of manu process & control, please include the typical production batch size. | Will request supplier to provide | Pending | Updated section S2.2 with below details provided in API-Annexure-III. Input: 270.00 ± 20.0 kg Theoretical molar yield: 237.65 ± 17.60 kg Expected molar yield: 195 ± 15.0 kg Molar Percentage yield: 82.05 ± 0.85% Percentage of yield range (with respect to obtained wt.): 0.72% | Ok, this point is cleared.
S2.3 | Control of Materials | Please provide this section. It is needed for submission. | Restricted part of DMF for API manufacturer. | Ok, this point is cleared. |  | Pending Updates from API Manufacturer if their DMF application has been accepted by HSA. Once accepted they should be able to provide us with the DMF number | Assigned DMF number 015:2027 | Ok, this point is cleared.
S2.4 | Controls of Critical Steps and Intermediates | Please provide this section. It is needed for submission. | Restricted part of DMF for API manufacturer. | Ok, this point is cleared. |  | Pending Updates from API Manufacturer if their DMF application has been accepted by HSA. Once accepted they should be able to provide us with the DMF number
S2.5 | Process Validation and/or Evaluation | Please provide this section. It is needed for submission. | Restricted part of DMF for API manufacturer. | Ok, this point is cleared. |  | Pending Updates from API Manufacturer if their DMF application has been accepted by HSA. Once accepted they should be able to provide us with the DMF number
S2.6 | Manufacturing Process Development | Please provide this section. It is needed for submission. | Restricted part of DMF for API manufacturer. | Ok, this point is cleared. |  | Pending Updates from API Manufacturer if their DMF application has been accepted by HSA. Once accepted they should be able to provide us with the DMF number
S4.1 | A) Specification of Drug Substance from drug product manufacturer | Using document: S4.1 Specification (dp), 1) please include the effective date of the document. 2) Please delete the test: Water content by KF (%, w/w) as it is a repeat. | Will request supplier to amend | Pending | 1. In S4.1 Specification (dp) effective date is mentioned. 2. Corrected part of S4.1 Specification provided in Annexure-IV | Ok, this point is cleared.
S4.2 | A) Analytical Procedures from drug product manufacturer | 1) Please provide the analytical procedures for these in-house methods: Description, Solubility, Residual on ignition, Phosphate content by potentiometry (on anhydrous), Residual solvents by GC (methanol, acetone, isopropyl alcohol, acetonitrile, methylene dichloride, methyl tertiary butyl ether, toluene, n—butanol, chloroform), acetic acid content by HPLC, NTPy/ NTTP nitrosamine impurity content by LC-MS 2) Please provide the compendial monographs for these compendial methods: identification by (UR, enantiometric purity by HPLC, phosphate test), water content by KF, enantiometric purity by HPLC (S-Enantiometer), Organic Impurities by HPLC (any individual impurity, total impurities), assay by HPLC (on anhydrous and solvent free basis) | Will request supplier to provide | Pending | 1) Analytical procedures of Sitagliptin Phosphate USP by FPP manufacturer provided in Annexure-V Below mentioned test parameters are not part of our specification, as these are not official in USP monograph-Residual on ignition & NTPy/ NTTP nitrosamine impurity content by LC-MS. 2) Compendial monographs provided in Annexure-VI | 1) For Annex IV, 1 analytical procedure – Residual on Ignition is missing. Please assist to add in this analytical procedure. | Pending | Please note that S4.2 needs to be from the dp manufacturer: Next Wave. Kindly assist again. | Attached | 1. Using attached document - S4.2 STP Sitagliptin Phospahte USP, please add in the analytical procedures for 1) Residue on Ignition, 2) Phosphate content by potientiometry and 3) NTPy/NTTP Nitrosamine impurities. | Attached Annex 1
S4.2 | A) Analytical Procedures from drug substance manufacturer | 1) Please provide the compendial monographs for these compendial methods: identification by (UR, enantiometric purity by HPLC, phosphate test), water content by KF, enantiometric purity by HPLC (S-Enantiometer), Organic Impurities by HPLC (any individual impurity, total impurities), assay by HPLC (on anhydrous and solvent free basis) | Will request supplier to provide | Pending | Compendial monographs provided in Annexure-VI Enantiomeric purity by HPLC, Organic impurities by HPLC have adopted from USP-NF Sitagliptin Phosphate. | Ok, this point is cleared.
S4.3 | A) Validation of Analytical Procedures from drug product manufacturer | Please provide separately from the DP manufacturer, the validation of analytical procedures for these in-house methods: Solubility, Residual on ignition, Phosphate content by potentiometry (on anhydrous), Residual solvents by GC (methanol, acetone, isopropyl alcohol, acetonitrile, methylene dichloride, methyl tertiary butyl ether, toluene, n—butanol, chloroform), acetic acid content by HPLC, NTPy/ NTTP nitrosamine impurity content by LC-MS | Will request supplier to provide | Pending | Analytical procedure of Sitagliptin is in line with USP monograph and drug substance manufacturer and methods are validated by the API manufacturer. So, validation report is not necessary. Residual on ignition & NTPy/ NTTP nitrosamine impurity content by LC-MS test are not part of FPP manufacturer API specification. | Sorry, this point is not addressed. S4.1 Specification (dp) provided by the dp manufacturer shows that these are in-house methods: Solubility, Residual on ignition, Phosphate content by potentiometry (on anhydrous), Residual solvents by GC (methanol, acetone, isopropyl alcohol, acetonitrile, methylene dichloride, methyl tertiary butyl ether, toluene, n—butanol, chloroform), acetic acid content by HPLC, NTPy/ NTTP nitrosamine impurity content by LC-MS. Validation test reports have to be provided for these in-house test methods to prove the method is suitable and accurate for its intended purpose. Kindly assist again. | AMV of Phosphate content by potentiometry (on anhydrous), Residual solvents by GC (methanol, acetone, isopropyl alcohol, acetonitrile, methylene dichloride, methyl tertiary butyl ether, toluene, n—butanol, chloroform), acetic acid content by HPLC, NTPy/ NTTP nitrosamine impurity content by LC-MS provided in Annex-1. As, Solubility & Residual on ignition test are not quantitative test, so AMV of these both test not performed. Also in specification of dp manufacturer indicate only In-house, not <In-house validated method>. | Ok, this point is cleared.
S4.3 | B) Validation of Analytical Procedures from drug substance manufacturer | Please provide in addition, the validation reports for these test methods: solubility, residual on ignition. | Will request supplier to provide | Pending | As the solubility and residue on ignition are not quantitative method parameters, the validation report for solubility and residue on ignition is not necessary. Hence, it is not applicable. | This point is cleared.
S7.1 | Stability Summary and Conclusions | 1. Using the document: S7.1 Stability Summary and Conclusions, please include in the conclusion of the stability studies, stress studies. 2. Please include in the site of manufacture for the stability batches. | Will request supplier to provide | Pending | 1. We have performed forced degradation studies and prepared the report separately. The stress study conclusion available in the forced degradation report. Hence, it is not necessary to include in 3.2.S.7.1 section. 2. The stability batches have been analysed at the same manufacturing site of API. | I think my request has been misunderstood. I am requesting to use the document: S7.1 Stability Summary and Conclusions to add in the additional information inside as the section on Conclusion is not seen in the document. 1. Using the document: S7.1 Stability Summary and Conclusions, please include a section about the conclusion of the stability studies, stress studies. 2. Please include in the site of manufacture for the stability batches. | Section S7.1 Stability Summary and Conclusions with including site of manufacturer & Conclusion of the stability studies, stress studies provided in Annex-2. | Ok, this point is cleared.
S7.2 | Post-approval Stability Protocol and Stability Commitment | Using the document: S7.2 Post-approval Stability Protocol and Stability Commitment, please add in the statement below:If any results fall outside of the retest / shelf-life specifications, these should be reported together with the proposed action/ CAPA. | Will request supplier to amend | Pending | The statement mentioned in 3.2.S.7.2 section has been included in line with ICH Q1A R2 guideline: “Stability Testing of New Drug Substances and Products”. Hence, there is no necessity to include the requested statement. | Absence of the statement is still not sufficient. If the supplier insists that no further change or update is needed, please be prepared for HSA further input requests or queries later during submission. | Section S7.2 Post-approval Stability Protocol and Stability Commitment with including commitment "If any results fall outside of the retest / shelf-life specifications, we will report these change immediately together with the proposed action/ CAPA" provided in Annex-3. | Ok, this point is cleared.
P3.2 | Description of Manufacturing Process And Process Controls | Using the document: P3.2 Description of Manufacturing Process And Process Controls, please include the proposed holding time for each process and accompanied by relevant supportive data. | Will request supplier to amend | Pending | Hold time data not available for this product, kindly submit dossier without hold time data - Next Wave Is it possible? | In any manufacturing processes, it is impossible to have zero (0) holding time. Will proceed with submission without holding time but no be prepared that HSA will raise back this question to the supplier (Next Wave) again. | Section P3.2 with including Hold time for both strengh (50 mg & 100 mg) provided in Annex-6. Hold time: Dispensing - 30 days Compression - 60 days Coating solution- 24 Hrs Coated tablet - 60 days Kindly note we have not performed hold time study for this product. | Ok, this point is cleared.
P5.1 | Specification(s) of Drug Product | Using document: P5.1 Specification(s) of Drug Product, please indicate clearly the release and stability indicating parameters. | Will request supplier to amend | Pending | Section P5.1 Specification(s) of Drug Product provided with release and stability indicating parameters in FP-Annex 2 | Ok, this point is cleared.
P5.2 | Analytical Procedures | Please submit a copy of compendial monographs for analytical procedures: Identification by UV Spectrum in PDA, Identifcation by HPLC, Uniformity of weight, Disintegration time, Uniformity of Dosage Units by HPLC, Dissolution of HPLC, Related substance by HPLC, Assay by HPLC. | Will request supplier to provide | Pending | Please find the compendial monographs of general chapter and Product monograph for analytical procedures in FP-Annex-3. | Please supply the remaining compendial monographs for analytical procedures: Uniformity of weight, Related substance by HPLC | General chapter 〈2091〉 Weight Variation of Dietary Supplements is applicable for Uniformity of weight & Organic Impurities mentioned in monograph is applicable for Related substance by HPLC in USP Mongraph Sitagliptin Tablet. General chapter 〈2091〉 & Mongraph Sitagliptin Tablet provided in Annex-4. | Ok, this point is cleared.
P5.3 | Validation of Analytical Procedures | Please submit the validation of analytical procedures for Microbial Examination Test. | Will request supplier to provide | Pending | Validation of analytical procedures for Microbial Examination Test provided in FP-Annex-4. | How about the validation of analytical procedures for Microbial Examination Test for Sitagliptin 100mg? Only documents for Sitagliptin 50mg is sighted | Attached in Folder P5.3 Validation Microbial USP 100mg | Ok, this point is cleared.
P7 | Container Closure System | Please submit declaration of compliance for the primary and secondary packaging. | Will request supplier to provide | Pending | Draft declaration of compliance for the primary and secondary packaging material provided in FP-Annex-5. Please check and confirm. | Declaration of Compliance has to be drafted and signed off by the Supplier of these Primary and Secondary packagings. A declaration of compliance to the appropriate international standards or pharmacopoeia, e.g. food contact EC/10/2011, Ph. Eur. Chapter 3, should be submitted. Please approach the suppliers of the primary and secondary packaging and ask for a Delcaration of Compliance. | Food grade declaration of Primary & secondary packing material provided in Annex-7 | All the delcaration of compliances have to include the appropriate international standards or pharmacopoeia, e.g. food contact EC/10/2011, Ph. Eur. Chapter 3. | Pending supplier reply or provide justification | Pending | Attached
P8.1 | Stability Summary and Conclusions | Using the document: P8.1 Stability Summary and Conclusions, 1. Please provide summary and conclusion of the stability studies, stress studies, storage condition. 2. Please include the stability information such as batch number, date of manufacture, container closure system. | Will request supplier to provide | Pending | Updated section P8.1 Stability Summary and Conclusions provided in FP-Annex-6. | Using the same document - P8.1 Stability Summary and Conclusions, under Stress Stability Study, please write down the conclusion results of this study. | Section P8.1, including conclusion for both strengh (50mg & 100 mg) provided in Annex-5. | Per document P8.1 (50mg and 100mg) - Stress Stability Study: Forced degradation studies used to establish degradation pathway based on the condition, high temperature, humidity, light, etc. Please give conclusion of results of the Forced degradation studies. Kindly delete the sentence: Stress stability study for this product Sitagliptin Tablets USP 50 mg is not applicable, hence stress stability not performed for this product, as this is not applicable. | Attached | For P8.1 , 50mg, under Conclusion, please delete "100mg". | Attached
P8.2 | Post-approval Stability Protocol and Stability Commitment | Using the document: P8.2 post approval stability protocol and stability commitment, please include the statement in page 1: . If any results fall outside of the retest / shelf-life specifications, these should be reported together with the proposed action. | Will request supplier to provide | Pending | Updated section P8.2 post approval stability protocol and stability commitment, provided in FP-Annex-7. | Please do the same for the document - P8.2 Post-approval Stability Protocol and Stability Commitment for (100mg). | Attached in Folder P8.2 Approval Stability Protocol USP 100mg | Ok, this point is cleared.

## API
Lee Pharma to Provide
1 | Proof of Approval | Please provide the approval letter in a colour scanned copy of either the original copy or a certified true copy of the original doc.
2 | GMP certificate | Please provide GMP certificate (PICs copy) from the API manufacturer (Lee Pharma).
3 | CEP | Please provide CEP from Lee Pharma, if its available.
4 | Description of Manufacturing Process and Process Controls | Using document: S2.2 Description of manu process & control, please include the typical production batch size.
5 | A) Specification of Drug Substance from drug product manufacturer | Using document: S4.1 Specification (dp), 1) please include the effective date of the document. 2) Please delete the test: Water content by KF (%, w/w) as it is a repeat.
6 | A) Analytical Procedures from drug product manufacturer | 1) Please provide the analytical procedures for these in-house methods: Description, Solubility, Residual on ignition, Phosphate content by potentiometry (on anhydrous), Residual solvents by GC (methanol, acetone, isopropyl alcohol, acetonitrile, methylene dichloride, methyl tertiary butyl ether, toluene, n—butanol, chloroform), acetic acid content by HPLC, NTPy/ NTTP nitrosamine impurity content by LC-MS 2) Please provide the compendial monographs for these compendial methods: identification by (UR, enantiometric purity by HPLC, phosphate test), water content by KF, enantiometric purity by HPLC (S-Enantiometer), Organic Impurities by HPLC (any individual impurity, total impurities), assay by HPLC (on anhydrous and solvent free basis)
7 | A) Analytical Procedures from drug substance manufacturer | 1) Please provide the compendial monographs for these compendial methods: identification by (UR, enantiometric purity by HPLC, phosphate test), water content by KF, enantiometric purity by HPLC (S-Enantiometer), Organic Impurities by HPLC (any individual impurity, total impurities), assay by HPLC (on anhydrous and solvent free basis)
8 | A) Validation of Analytical Procedures from drug product manufacturer | Please provide separately from the DP manufacturer, the validation of analytical procedures for these in-house methods: Solubility, Residual on ignition, Phosphate content by potentiometry (on anhydrous), Residual solvents by GC (methanol, acetone, isopropyl alcohol, acetonitrile, methylene dichloride, methyl tertiary butyl ether, toluene, n—butanol, chloroform), acetic acid content by HPLC, NTPy/ NTTP nitrosamine impurity content by LC-MS
9 | B) Validation of Analytical Procedures from drug substance manufacturer | Please provide in addition, the validation reports for these test methods: solubility, residual on ignition.
10 | Stability Summary and Conclusions | 1. Using the document: S7.1 Stability Summary and Conclusions, please include in the conclusion of the stability studies, stress studies. 2. Please include in the site of manufacture for the stability batches.
11 | Post-approval Stability Protocol and Stability Commitment | Using the document: S7.2 Post-approval Stability Protocol and Stability Commitment, please add in the statement below:If any results fall outside of the retest / shelf-life specifications, these should be reported together with the proposed action/ CAPA.

## DP
Next Wave (DP) Gap
1 | Description of batch numbering system | Please provide the Batch Numbering System SOP.
2 | Description of Manufacturing Process And Process Controls | Using the document: P3.2 Description of Manufacturing Process And Process Controls, please include the proposed holding time for each process and accompanied by relevant supportive data.
3 | Specification(s) of Drug Product | Using document: P5.1 Specification(s) of Drug Product, please indicate clearly the release and stability indicating parameters.
4 | Analytical Procedures | Please submit a copy of compendial monographs for analytical procedures: Identification by UV Spectrum in PDA, Identifcation by HPLC, Uniformity of weight, Disintegration time, Uniformity of Dosage Units by HPLC, Dissolution of HPLC, Related substance by HPLC, Assay by HPLC.
5 | Validation of Analytical Procedures | Please submit the validation of analytical procedures for Microbial Examination Test.
6 | Container Closure System | Please submit declaration of compliance for the primary and secondary packaging.
7 | Stability Summary and Conclusions | Using the document: P8.1 Stability Summary and Conclusions, 1. Please provide summary and conclusion of the stability studies, stress studies, storage condition. 2. Please include the stability information such as batch number, date of manufacture, container closure system.
8 | Post-approval Stability Protocol and Stability Commitment | Using the document: P8.2 post approval stability protocol and stability commitment, please include the statement in page 1: . If any results fall outside of the retest / shelf-life specifications, these should be reported together with the proposed action.